## WBS
Work Breakdown Structure
Student's Name |  |  |  |  | Date
Instructor's Name |  |  |  |  | Milestone #
Language
Task Number | Description | Inputs From | Outputs To | Planned Value | Earned Value | Hours | Cum. Hours | Date

## WBS Diagram
Work Breakdown Structure
PROGLAN PROJECT | [5 empty] | OTHER PROJECT TOOLS
Level 1 WBS |  |  | Compiler Project |  |  | Project Name
Level 2 WBS | Initiation Phase | Planning Phase | Execution Phase | Controlling Phase | Closing Phase | Phase
Level 3 WBS | Project Evaluation | Project Management | Project Management | Project Management | Project Management | Task
| Other | Requirements | Evaluation & Selection | Other | Other
| Other | Other | Design | Other | Other
| Other | Other | Build | Other | Other
| Other | Other | Test | Other | Other
| Other | Other | Training | Other | Other
Implementation
Stabilization
Other

## RWT
REQUIREMENTS TEMPLATE
Student's Name |  |  |  |  | Date
Instructor's Name |  |  |  |  | Milestone #
Language
Requirement# | Criteria/Category/ Functional Activity | Inputs |  |  | Comments
|  | Test Case Reference | Code Module Reference | Milestone Document Reference

## SPT
SCHEDULE PLANNING TEMPLATE
Student's Name |  |  |  | Date
Instructor's Name |  |  |  | Program #
Day/Week |  | Plan |  | Actual
No. | Date | Hours | Cum. Hours | Hours | Cum. Hours | Cum. EV | Adj. EV

## TRT
TIME RECORDING LOG
Student's Name | PJ Cardenas |  |  |  | Date | 2010-02-19
Instructor's Name | R Lagdaan |  |  |  | Program #
[5 empty] | Language | C#
Date | Start(m) | Stop(m) | ∆ Time(m) | Phase |  | Comments
2010-02-16 | 20:15 | 22:15 | 2 | Execution |  | Coding: Scanner
2010-02-17 | 13:30 | 16:30 | 3 | Execution |  | Coding: Scanner
2010-02-17 | 21:30 | 23:30 | 2 | Execution |  | Bug fixing: Scanner
2010-02-18 | 22:00 | 23:00 | 1 | Execution |  | Bug fixing: Scanner
2010-02-20 | 8:00 | 11:00 | 3 | Execution |  | Coding: Parser

## TUL
Time Utilization Log
Student's Name | PJ Cardenas |  | Date | 2010-02-19
Instructor's Name | R Lagdaan |  | Program #
Task |  | Planned Value |  |  | Earned Value
No. | Name | Hours | Cum. Hours | Date | Date | Cum. Hours
1 | CP(1) | 0.25 | 0.25 | 2010-02-15 | 2010-02-15 | 0.25
2 | CP(2) | 0.25 | 0.5 | 2010-02-15 | 2010-02-15 | 0.5
3 | C(1) | 2 | 2.5 | 2010-02-15 | 2010-02-15 | 2.5
4 | C(2) | 2 | 4.5 | 2010-02-15 | 2010-02-15 | 4.5
5 | D(6) | 2 | 6.5 | 2010-02-15 | 2010-02-15 | 6.5
6 | CP(3) | 0.25 | 6.75 | 2010-02-16 | 2010-02-16 | 6.75
7 | CP(4) | 0.25 | 7 | 2010-02-16 | 2010-02-16 | 7
8 | C(3) | 2 | 7.5 | 2010-02-16 | 2010-02-16 | 7.5
9 | C(4) | 2 | 9.5 | 2010-02-16 | 2010-02-16 | 9.5
10 | CT(6) | 2 | 11.5 | 2010-02-16 | 2010-02-16 | 11.5
11 | CT(6) | 5 | 16.5 | 2010-02-17 | 2010-02-17 | 16.5
12 | D(6) | 1 | 17.5 | 2010-02-17 | 2010-02-17 | 17.5
13 | CP(1) | 0.25 | 17.75 | 2010-02-18 | 2010-02-18 | 17.75
14 | CP(2) | 0.25 | 18 | 2010-02-18 | 2010-02-18 | 18
15 | C(1) | 2 | 20 | 2010-02-18 | 2010-02-18 | 20
16 | C(2) | 2 | 22 | 2010-02-18 | 2010-02-18 | 22
17 | CT(6) | 1 | 23 | 2010-02-18 | 2010-02-18 | 23
18 | CP(3) | 0.25 | 23.25 | 2010-02-19 | 2010-02-19 | 23.25
19 | CP(4) | 0.25 | 23.5 | 2010-02-19 | 2010-02-19 | 23.5
20 | C(3) | 2 | 25.5 | 2010-02-19 | 2010-02-19 | 25.5
21 | C(4) | 2 | 27.5 | 2010-02-19 | 2010-02-19 | 27.5
22 | CP(5) | 1 | 28.5 | 2010-02-19 | 2010-02-19 | 28.5
23 | C(5) | 4 | 32.5 | 2010-02-19 | 2010-02-19 | 32.5
24 | CP(6) | 0.5 | 33 | 2010-02-20 | 2010-02-20 | 33
25 | C(6) | 1 | 34 | 2010-02-20 | 2010-02-20 | 34
26 | CT(6) | 3 | 37 | 2010-02-20 | 2010-02-20 | 37
27 | U(6) | 2 | 39 | 2010-02-20 | 2010-02-20 | 39
| CODE | MEANING
| nnn | Class #
| CP(nnn) | Preparing for Class nnn
| C(nnn) | Attending Class nnn
| D(nnn) | Designing Programs for Class nnn
| CT(nnn) | Coding and Testing for Class nnn
| U(nnn) | Documenting for Class nnn

## DLT
Defect Log Template
Student's Name |  |  |  |  | Date
Instructor's Name |  |  |  |  | Milestone #
Language
Defect No. | Created By | Date | Type | Owner | Assigned Date | Status | Cause | Resolution | Resolution Date | Estimated Time to Fix | Actual Time to Fix
Cause Code | Defect Tyoe | Description
| 10 | Documentation comments, messages
ed(education) | 20 | Syntax spelling, punctuations, formats
co(communication) | 30 | Build, package change management, library, version control
ov(oversight) | 40 | Assignment declaration, duplicate names, scope, limits
tr(transcription) | 50 | Interface procedure calls and references, I/O, user formats
pr(process) | 60 | Checking error messages, inadequate checks
| 70 | Data structure, content
| 80 | Function login, pointers, loops, recursion, computation
| 90 | System configuration, timing, memory
| 100 | Environment design, compile, test, other support system problems