## WBS
Work Breakdown Structure
Group Name | The Elites |  |  |  | Date | 2010-05-03
Instructor's Name | Randy Lagdaan |  |  |  | Milestone # | 2
[5 empty] | Language | C#
Task Number | Description | Planned Value | Earned Value | Hours | Cum. Hours | Date
1 | Scanner() constructor | 5 | 6 | 4 | 4 | 2010-02-15
2 | Init() function | 2 | 2 | 1 | 5 | 2010-02-15
3 | GetToken() function | 2 | 2 | 1 | 6 | 2010-02-15
4 | Scan() function | 4 | 4 | 3 | 9 | 2010-02-16
5 | LookAhead() function | 3 | 3 | 10 | 19 | 2010-02-17
6 | Token Class | 20 | 20 | 10 | 29 | 2010-02-18

## WBS Diagram
The Elites
PROGLAN PROJECT
Level 1 WBS |  |  | Tiny C Compiler dotNET |  |  | Project Name
Level 2 WBS | Lexical Analyzer | Syntactic Analyzer | Semantic Analyzer | Executable file Creator | Installer | Work Scopes
Level 3 WBS | Init() | Parser() | Not yet determined | Not yet determined | Not yet determined | Tasks
| Scan() | Parse()
| GetToken() | Parse function for every EBNF production
LookAhead()
Token Object
Scanner()

## RWT (hidden)
REQUIREMENTS TEMPLATE
Group Name | The Elites |  |  |  | Date
Instructor's Name | Randy Lagdaan |  |  |  | Milestone # | 2
Language
Requirement# | Criteria/Category/ Functional Activity | Inputs |  |  | Comments
|  | Test Case Reference | Code Module Reference | Milestone Document Reference
Scanner and Lexer | the scanner is a tokenizer that stores each token in a lexeme | testscipt.xslx | tccconsole.sln | Milestone II and III.docx

## TRL (AIVAN)
TIME RECORDING LOG
Student's Name | Aivan Monceller |  |  |  | Date | 2010-03-05
Instructor's Name | Randy Lagdaan |  |  |  | Program #
[5 empty] | Language | C#
Date | Start(m) | Stop(m) | ∆ Time(m) | Phase |  | Comments
2010-03-01 | 9:00 | 11:00 | 2 | Execution |  | Coding: Parser
2010-03-01 | 21:00 | 23:00 | 2 | Execution |  | Bug fixing: Parser
2010-03-04 | 13:00 | 15:00 | 2 | Execution |  | Bug fixing: Parser
2010-03-04 | 22:00 | 23:00 | 1 | Execution |  | Bug fixing: Parser

## TRL(PETER)
TIME RECORDING LOG
Student's Name | Busto, Peter Richard F. |  |  |  | Date | 2010-03-05
Instructor's Name | Randy Lagdaan |  |  |  | Program #
[5 empty] | Language | C#.NET
Date | Start(m) | Stop(m) | ∆ Time(m) | Phase |  | Comments
2010-03-02 | 13:00 | 17:00 | 4 | Execution |  | Coding: Parser
2010-03-02 | 20:00 | 23:00 | 3 | Execution |  | Coding: Parser
2010-03-03 | 11:00 | 13:00 | 2 | Execution |  | Bug fixing: Parser
2010-03-04 | 13:00 | 16:00 | 3 | Execution |  | Bug fixing: Parser
2010-03-05 | 12:00 | 15:30 | 3.5 | Execution |  | Test Script

## TRL(PJ)
TIME RECORDING LOG
Student's Name | PJ Cardenas |  |  |  | Date | 2010-03-05
Instructor's Name | R Lagdaan |  |  |  | Program #
[5 empty] | Language | C#
Date | Start(m) | Stop(m) | ∆ Time(m) | Phase |  | Comments
2010-03-03 | 20:15 | 22:15 | 2 | Execution |  | Coding: Parser
2010-03-04 | 13:30 | 16:30 | 3 | Execution |  | Coding: Parser
2010-03-04 | 21:30 | 23:30 | 2 | Execution |  | Bug fixing: Parser
2010-03-04 | 22:00 | 23:00 | 1 | Execution |  | Bug fixing: Parser
2010-03-05 | 8:00 | 11:00 | 3 | Execution |  | Coding: Parser

## TUL(AIVAN)
Time Utilization Log
Student's Name | Aivan Monceller |  | Date | 2010-03-05
Instructor's Name | Randy Lagdaan |  | Program #
Task |  | Planned Value |  |  | Earned Value
No. | Name | Hours | Cum. Hours | Date | Hours | Cum. Hours | Date
1 | CT(PROGLAN) | 3 | 3 | 2010-02-15 | 3 | 3 | 2010-02-15
2 | CT(SOFTDEV) | 3 | 6 | 2010-02-15 | 2 | 5 | 2010-02-15
3 | CP(SOCPSY) | 1 | 7 | 2010-02-15 | 0.3 | 5.3 | 2010-02-15
5 | CP(ECONTAX) | 0.3 | 7.3 | 2010-02-16 | 0.25 | 5.55 | 2010-02-16
6 | C(ECONTAX) | 2 | 9.3 | 2010-02-16 | 2 | 7.55 | 2010-02-16
7 | C(SOCPSY) | 2 | 11.3 | 2010-02-16 | 2 | 9.55 | 2010-02-16
8 | D(PROGLAN) | 1 | 12.3 | 2010-02-16 | 0.3 | 9.85 | 2010-02-16
9 | CP(RIZLIFE) | 2 | 14.3 | 2010-02-17 | 2 | 11.85 | 2010-02-17
10 | C(RIZLIFE) | 2 | 16.3 | 2010-02-17 | 2 | 13.85 | 2010-02-17
11 | C(SOFTDEV) | 2 | 18.3 | 2010-02-17 | 2 | 15.85 | 2010-02-17
12 | CT(PROGLAN) | 3 | 21.3 | 2010-02-18 | 2 | 17.85 | 2010-02-18
13 | CT(SOFTDEV) | 3 | 24.3 | 2010-02-18 | 0.3 | 18.15 | 2010-02-18
14 | CP(ECONTAX) | 0.3 | 24.6 | 2010-02-19 | 0.3 | 18.45 | 2010-02-19
15 | C(ECONTAX) | 2 | 26.6 | 2010-02-19 | 2 | 20.45 | 2010-02-19
16 | C(SOCPSY) | 2 | 28.6 | 2010-02-19 | 2 | 22.45 | 2010-02-19
17 | C(MINSYST) | 4 | 32.6 | 2010-02-19 | 4 | 26.45 | 2010-02-19
18 | CP(PROGLAN) | 2 | 34.6 | 2010-02-20 | 2 | 28.45 | 2010-02-20
19 | C(PROGLAN) | 1 | 35.6 | 2010-02-20 | 1 | 29.45 | 2010-02-20
20 | D(PROGLAN) | 1 | 36.6 | 2010-02-20 | 1 | 30.45 | 2010-02-20
21 | CP(RIZLIFE) | 3 | 39.6 | 2010-02-20 | 2 | 32.45 | 2010-02-20
22 | C(RIZLIFE) | 2 | 41.6 | 2010-02-20 | 2 | 34.45 | 2010-02-20
23 | C(SOFTDEV) | 2 | 43.6 | 2010-02-20 | 2 | 36.45 | 2010-02-20
| CODE | MEANING
| nnn | Class #
| CP(nnn) | Preparing for Class nnn
| C(nnn) | Attending Class nnn
| D(nnn) | Designing Programs for Class nnn
| CT(nnn) | Coding and Testing for Class nnn
| U(nnn) | Documenting for Class nnn

## TUL(PETER)
Time Utilization Log
Student's Name | Peter Richard Busto |  | Date | 2010-03-05
Instructor's Name | Randy Lagdaan |  | Program # | ________________
Task |  | Planned Value |  |  | Earned Value
No. | Name | Hours | Cum. Hours | Date | Date | Hours | Cum. Hours
1 | CP(ECONTAX) | 1 | 1 | 2010-02-15 | 2010-02-15 | 0.5 | 0.5 | Notation | Explanation
2 | C(SOCPSYC) | 2 | 3 | 2010-02-15 | 2010-02-15 | 2 | 2.5 | nnn | Class number
3 | C(ECONTAX) | 2 | 5 | 2010-02-15 | 2010-02-15 | 2 | 4.5 | CP(nnn) | Preparing for Class nnn
4 | CP(RIZLIFE) | 2 | 7 | 2010-02-15 | 2010-02-15 | 3 | 7.5 | C(nnn) | Attending Class nnn
5 | CP(RIZLIFE) | 1 | 8 | 2010-02-16 | 2010-02-16 | 1 | 8.5 | D(nnn) | Designing programs for Class nnn
6 | CT(PROGLAN) | 10 | 18 | 2010-02-16 | 2010-02-16 | 7 | 15.5 | CT(nnn) | Coding and testing for Class nnn
7 | CP(RIZLIFE) | 1 | 19 | 2010-02-17 | 2010-02-17 | 0.75 | 16.25 | U(nnn) | Documenting programs for Class nnn
8 | CP(SOFTDEV) | 0.5 | 19.5 | 2010-02-17 | 2010-02-17 | 1 | 17.25
9 | C(RIZLIFE) | 2 | 21.5 | 2010-02-17 | 2010-02-17 | 2 | 19.25
10 | C(SOFTDEV) | 2 | 23.5 | 2010-02-17 | 2010-02-17 | 2 | 21.25
11 | CP(ECONTAX) | 1 | 24.5 | 2010-02-18 | 2010-02-18 | 0.25 | 21.5
12 | C(SOCPSYC) | 2 | 26.5 | 2010-02-18 | 2010-02-18 | 2 | 23.5
13 | C(ECONTAX) | 2 | 28.5 | 2010-02-18 | 2010-02-18 | 2 | 25.5
14 | C(MINSYST) | 4 | 32.5 | 2010-02-18 | 2010-02-18 | 2 | 27.5
15 | CP(RIZLIFE) | 2 | 34.5 | 2010-02-19 | 2010-02-19 | 3 | 30.5
16 | CT(PROGLAN) | 10 | 44.5 | 2010-02-19 | 2010-02-19 | 7 | 37.5
17 | C(PROGLAN) | 1 | 45.5 | 2010-02-20 | 2010-02-20 | 1 | 38.5
18 | U(PROGLAN) | 3 | 48.5 | 2010-02-20 | 2010-02-20 | 3 | 41.5
19 | C(RIZLIFE) | 2 | 50.5 | 2010-02-20 | 2010-02-20 | 2 | 43.5
20 | C(SOFTDEV) | 2 | 52.5 | 2010-02-20 | 2010-02-20 | 2 | 45.5

## TUL(PJ)
Time Utilization Log
Student's Name | PJ Cardenas |  | Date | 2010-03-05
Instructor's Name | R Lagdaan |  | Program #
Task |  | Planned Value |  |  | Earned Value
No. | Name | Hours | Cum. Hours | Date | Hours | Date | Cum. Hours
1 | CP(1) | 0.25 | 0.25 | 2010-02-15 | 0.25 | 2010-02-15 | 0.25 | CODE | MEANING
2 | CP(2) | 0.25 | 0.5 | 2010-02-15 | 0.25 | 2010-02-15 | 0.5 | nnn | Class #
3 | C(1) | 2 | 2.5 | 2010-02-15 | 2 | 2010-02-15 | 2.5 | CP(nnn) | Preparing for Class nnn
4 | C(2) | 2 | 4.5 | 2010-02-15 | 2 | 2010-02-15 | 4.5 | C(nnn) | Attending Class nnn
5 | D(6) | 2 | 6.5 | 2010-02-15 | 2 | 2010-02-15 | 6.5 | D(nnn) | Designing Programs for Class nnn
6 | CP(3) | 0.25 | 6.75 | 2010-02-16 | 0.25 | 2010-02-16 | 6.75 | CT(nnn) | Coding and Testing for Class nnn
7 | CP(4) | 0.25 | 7 | 2010-02-16 | 0.25 | 2010-02-16 | 7 | U(nnn) | Documenting for Class nnn
8 | C(3) | 2 | 7.5 | 2010-02-16 | 2 | 2010-02-16 | 7.5
9 | C(4) | 2 | 9.5 | 2010-02-16 | 2 | 2010-02-16 | 9.5
10 | CT(6) | 2 | 11.5 | 2010-02-16 | 2 | 2010-02-16 | 11.5
11 | CT(6) | 5 | 16.5 | 2010-02-17 | 5 | 2010-02-17 | 16.5
12 | D(6) | 1 | 17.5 | 2010-02-17 | 1 | 2010-02-17 | 17.5
13 | CP(1) | 0.25 | 17.75 | 2010-02-18 | 0.25 | 2010-02-18 | 17.75
14 | CP(2) | 0.25 | 18 | 2010-02-18 | 0.25 | 2010-02-18 | 18
15 | C(1) | 2 | 20 | 2010-02-18 | 2 | 2010-02-18 | 20
16 | C(2) | 2 | 22 | 2010-02-18 | 2 | 2010-02-18 | 22
17 | CT(6) | 1 | 23 | 2010-02-18 | 1 | 2010-02-18 | 23
18 | CP(3) | 0.25 | 23.25 | 2010-02-19 | 0.25 | 2010-02-19 | 23.25
19 | CP(4) | 0.25 | 23.5 | 2010-02-19 | 0.25 | 2010-02-19 | 23.5
20 | C(3) | 2 | 25.5 | 2010-02-19 | 2 | 2010-02-19 | 25.5
21 | C(4) | 2 | 27.5 | 2010-02-19 | 2 | 2010-02-19 | 27.5
22 | CP(5) | 1 | 28.5 | 2010-02-19 | 1 | 2010-02-19 | 28.5
23 | C(5) | 4 | 32.5 | 2010-02-19 | 4 | 2010-02-19 | 32.5
24 | CP(6) | 0.5 | 33 | 2010-02-20 | 0.5 | 2010-02-20 | 33
25 | C(6) | 1 | 34 | 2010-02-20 | 1 | 2010-02-20 | 34
26 | CT(6) | 3 | 37 | 2010-02-20 | 3 | 2010-02-20 | 37
27 | U(6) | 2 | 39 | 2010-02-20 | 2 | 2010-02-20 | 39

## DLT
Defect Log Template
Student's Name | The Elites |  |  |  | Date | 2010-03-05
Instructor's Name | Randy Lagdaan |  |  |  | Milestone # | 2
[5 empty] | Language | C#.NET
Defect No. | Created By | Date | Type | Owner | Assigned Date | Status | Cause | Resolution | Resolution Date | Estimated Time to Fix | Actual Time to Fix | Description
1 | AM | 2010-02-02 | 80 | PB | 2010-02-16 | In-Progress | ov |  | 2010-02-23 | 13:00-15:00 |  | main() with no arguments is not working
2 | AM | 2010-02-11 | 80 | AM | 2010-02-16 | In-Progress | tr |  | 2010-02-22 | 21:00-22:00 |  | FOR loop craze
3 | PB | 2010-02-16 | 60 | PB | 2010-02-16 | New | ov |  | 2010-02-23 | 15:00-16:00 |  | getch() is not working
4 | PC | 2010-02-16 | 60 | PC | 2010-02-16 | New | ov |  | 2010-02-24 | 15:00-16:00 |  | using prefix and postfix
5 | PB | 2010-02-19 | 40 | PB | 2010-02-19 | In-Progress | ov |  | 2010-02-23 | 16:00-17:00 |  | character assigment is not working
Cause Code | Defect Type | Description | [5 empty] | Aivan Monceller |  | AM
| 10 | Documentation comments, messages | [5 empty] | Patrick Joseph Cardenas |  | PC
ed(education) | 20 | Syntax spelling, punctuations, formats | [5 empty] | Peter Richard Busto |  | PB
co(communication) | 30 | Build, package change management, library, version control
ov(oversight) | 40 | Assignment declaration, duplicate names, scope, limits
tr(transcription) | 50 | Interface procedure calls and references, I/O, user formats
pr(process) | 60 | Checking error messages, inadequate checks
| 70 | Data structure, content
| 80 | Function login, pointers, loops, recursion, computation
| 90 | System configuration, timing, memory
| 100 | Environment design, compile, test, other support system problems
Status
New
In-Progress
Under Review
Completed

## SPT (hidden)
SCHEDULE PLANNING TEMPLATE
Student's Name |  |  |  | Date
Instructor's Name |  |  |  | Program #
Day/Week |  | Plan |  | Actual
No. | Date | Hours | Cum. Hours | Hours | Cum. Hours | Cum. EV | Adj. EV